## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Assigned
|  |  | Day 1 | Day 2 | Day 3 | Day 4
Add Stock | Require compartment to be selected | 4 |  |  |  |  | Guv
View Stock | Add a file save system .csv (file) | 3 |  |  |  |  | Yeni
Add Stock | Add another attribute to the compartment class | 2 | 0 |  |  |  | Jess
Cook | Create Cook Landing Page, and View Food Page | 3 |  |  |  |  | Guv
Cook | Add a CookLandingPageCodeBehind and implement | 5 | 5 | 0 |  |  | Justice
Cook | Add a ViewFoodCodeBehind and implement | 5 | 4.5 | 4.5 | 2 | 0 | Jess
View Stock | Add Remove Stock Button for the Quartermaster (functionality) | 3 |  |  |  |  | Guv
Cook | Add Get Food button functionality | 4 |  |  |  |  | Yeni
System | Implement better password security | 3 | 3 | 3 | 0 |  | Justice
System | System Lockout after 5 failed authentication attempts | 3 |  |  |  |  | Yeni
| Estimate Totals | 31 | 12.5 | 7.5 | 2 | 0 | 0